## Sheet1
HARMONY GROUND ZERO LIST
ITEM | ADDRESS | SCHEDULED | COMPLETED | NOTES
WHIP GRASS AT EDGE OF NATURAL AREA | LEAVING GERHARDS OFFICE AREA | WEEK OF OCTOBER 3RD
EDGE TREE RINGS | LEAVING GERHARDS OFFICE AREA | WEEK OF OCTOBER 10TH |  | MAINTAIN BI-WEEKLY THEREAFTER
SCREEN AREA FOR SOD REPLACEMENT | E FIVE OAKS AREA | DECEMBER
SCREEN AREA FOR SOD REPLACEMENT | ACROSS FROM SECTION 0 | DECEMBER |  | POSSIBLE DEVELOPER ISSUES HERE ALSO
BED WEEDS | ACROSS FROM SECTION 0 | WEEK OF OCTOBER 10TH |  | MAINTAIN BI-WEEKLY THEREAFTER
REMOVE TREE SUCKERS | ACROSS FROM SECTION 0 | WEEK OF OCTOBER 10TH |  | MAINTAIN BI-WEEKLY THEREAFTER
REPLACE SALVIA | E FIVE OAKS AREA | OCTOBER |  | WARRANTY WORK
PREPARE PLAN FOR DECLINING TREES | E FIVE OAKS AREA | WEEK OF OCTOBER 10TH
WEEDS IN EVERGREENS SHRUBS | E FIVE OAKS AREA | WEEK OF OCTOBER 3RD |  | MAINTAIN BI-WEEKLY BY SPRAYING FUSALATE OR SUGGESTED MATERIAL FOR EACH TYPE OF SHRUB OR PERENNIAL THEREAFTER
REMOVE DEAD TREE | BARK CENTRAL | WEEK OF OCTOBER 3RD
SCREEN AREA FOR SOD REPLACEMENT | FRONT OF SWIM CLUB | DECEMBER
KEEP SHRUBS OFF POOL FENCE | SWIM CLUB | WEEK OF OCTOBER 10TH
PREPARE ACTION PLAN WITH PICTURES FOR TREES/SHRUBS/ANIMAL DAMAGE | TOWN SQUARE | WEEK OF OCTOBER 3RD |  | ITEMS FOUND DURING LAST WEEKS INSPECTION BY DAVEY TREE
SCREEN AREA FOR SOD REPLACEMENT | TOWN SQUARE | DECEMBER
SCREEN FOR SOD REPLACEMENT | ASHLEY PARK | DECEMBER
TOUCH UP JACK FROST PLANTS | FIVE OAKS TH | WEEK OF OCTOBER 3RD
REPLACE NEW MAGNOILA W/BIGGER | FIVE OAKS TH | WEEK OF OCTOBER 10TH
SCAN FOR SOD REPLACEMENT | CLAYBRICK | DECEMBER
REMOVE DEAD TREE | PRIMROSE | WEEK OF OCTBER 3RD
SCAN FOR SOD REPLACEMENT | CATBRIAR | DECEMBER
REPLACE FORMOSA | CATBRIAR | WEEK OF OCTOBER 26TH
REPLACE 6 AZALEAS | CATBRIAR | WEEK OF OCTOBER 26TH
WEEDS IN BEDS | WILLOW DOG PARK | WEEK OF OCTOBER 3RD
CLEAN UP LINE ALONG FENCE/SPRAY | WILLOW DOG PARK | WEEK OF OCTOBER 3RD
REMOVE VINES FROM SHRUBS | WILLOW DOG PARK | WEEK OF OCTOBER 3RD
TREE LARGER SHRUBS | WILLOW DOG PARK | WEEK OF OCTOBER 10TH
WEEDS IN BEDS | WILLOW DOG PARK | WEEK OF OCTOBER 3RD
MORE CONSISTENT ANT CONTROL | WILLOW DOG PARK | WEEK OF OCTOBER 3RD |  | WILL ALSO PUT DOWN DIVION IN OCTOBER
SPARY DRIVEWAY | ADJACENT TO WILLOW DOG | WEEK OF OCTOBER 3RD
REPLACE TREE | 7104 INDIAN GRASS | WEEK OF OCTOBER 10TH
REPLACE OAK TREE | 7121 INDIAN GRASS | WEEK OF OCTOBER 10TH
LOOK AT TRIMMING/HEALTH PLAN FOR CREPE MYRTLE | GOPHER APPLE PARK | WEEK OF OCTOBER 10TH
SPRAY & CLEAN UP PATHWAY TO NATURE AREA | PARK | WEEK OF OCTOBER 3RD
SCREEN FOR SOD REPLACEMENT | SCHOOLHOUSE POCKET PARK | DECEMBER
CHECK SHRUBS FOR BETTER MAINTENANCE PLAN | SCHOOLHOUSE POCKET PARK | OCTOBER 3RD
CONSISTENT ANT SPRAY | SOCCER FIELDS | OCTOBER 3RD |  | WILL ALSO PUT DOWN DIVION IN OCTOBER
WINTER PREP SOCCER FIELDS | SOCCER FIELDS | NOVEMBER |  | CUT GRASS SHORT, AERATION, OVERSEEDING WITH RYE, MUST BE 50 DEGREES AT NIGHT PRIOR TO OVERSEEDING, EXTRA CHARGE
DECLINING TREES | BEHIND SUNDIAL PARK | WEEK F OCTOBER 19TH |  | EXTRA FERTILIZATION, ROTTING FROM TOO MUCH WATER
SCREEN FOR SOD REPLACEMENT | SUNDIAL PARK | DECEMBER
INSTALL GOLD MOUND | SUNDAIL PARK | NOVEMBER |  | REMOVE SOD, INSTALL GOLD MOUND INSTEAD 50/50 SPLIT
KNOCK DOWN WET AREA IN DITCH | CHERRY HILL | WEEK OF OCTOBER 3RD |  | BI-WEEKLY THEREAFTER
REMOVE & SPRAY WEEDS | PLAYGROUND GREEN AREA | WEEK OF OCTOBER 3RD
WEED & TRIM SHRUBS | GREEN AREA | WEEK OF OCTOBER 3RD
SCREEN FOR SOD REPLACEMENT | BLAZING STAR AT CORNER OF GREEN NEIGHBORHOOD | DECEMBER
WEED BEDS ALONG 192 FENCE | 192 FENCE LINE | WEEK OF OCTOBER 10TH
CUT BACK GRASSES | BEHIND MAIN ENTRY BEDS | WEEEK OF OCTOBER 10TH