## Data
Harmony Community Development District
Field Services Monthly Wetland Report
# | Maintenance Area Name | Acres | Invasive Species | 2019-11-13 | Treatment Status
| Map Tab Shows Local QuickMap |  | Vegitation Identification | (End-of-Month Status) | Pending Activities
| Click Links Below For Internet Maps |  | Infestation Severity High, Medium, Low | Prescribed Treatment | Percent Complete
1 | Buck Lake - South | 1.4 | Lygodium High | Spraying only with mixture of RoundUp and Cutrine. | 50 percent complete at this time. Will be done in early December.
2 | Green - South | 1 | Grapevine Medium | Sprayed with RoundUp and cut the vines running up the base of the tree. | 100 percent complete.
3 | Golf Course - West | 2.3 | Lygodium High
4 | Golf Course - East | 3.7 | Lygodium High
5 | Golf Course - South | 2.8 | Grapevine Medium
6 | The Lakes - East | 3.1 | Lygodium High
7 | {Future} | -- | ----
8 | {Future} | -- | ----
9 | {Future} | -- | ----
10 | {Future} | -- | ----
11 | {Future} | -- | ----
12 | {Future} | -- | ----
13 | {Future} | -- | ----
14 | {Future} | -- | ----
15 | {Future} | -- | ----
| TOTAL ACRES | 102.3165 | Total size (in acres) of all foliage maintenance areas
| AVG. TREATED ACRES | 20.4633 | Average infested foliage treated area is roughly 20 %
| Additonal Notes: | This month we have finished up the treatment of the lygodium in the area that runs along Dark Sky that backs up to Goldflower Avenue. This was about a total of three weeks of going through and cutting all vines reachable and spraying with Roundup after. Once we started to visibly see the grape vines dying we went back to where we started and retreated anything that was missed or we could not reach the first time. We have now begun the treatment of lygodium alondg Buck Lake which is mostly requiring sparing of the fern and some cutting but mostly just to make a path way to get the hose and sprayer back far enough to reach all the way back towards lake. Results are looking very well everything we are spraying is dying off and the following week we are going back to same location to check and retreat any ares missed. There are very large areas of the lygodium so it is hard to get to all of one area at one time so we are making sure to follow up on all the areas to ensure all has been treated.

## Map
Data!A1 | BACK

## MASTER (hidden)
Harmony CDD Monthly Pond Report
Pond # |  | Name | Acres | Duckweed | Algae | Cattail | Pennywort | Grasses | Spatterdock | Remarks | Treatment Plan
Map Quickview, click here. Internet access not required |  |  |  | SEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevance | [5 empty] | Color Code: ----> | Treated, current month
| Map links below require internet | [9 empty] | Treatment Needed
1 | H-1 |  | 1.4
2 | H1 |  | 1
3 | H-1 |  | 2.3
4 | H-2 |  | 3.7
5 | Cherry Hill |  | 2.8
6 | S. Long Pond |  | 3.1
7 | N. Long Pond |  | 3.1
8 | Dog Park Tr. |  | 3.5
9 | Dog Park Tr. |  | 1
10 | Dog Park |  | 3
11 | Estates N. |  | 1.8
12 | Estates S. |  | 1.7
13 | Golf Course |  | 1.5
14 | Golf Course |  | 1.5
15 | Golf Course |  | 4
16 | Golf Course |  | 3.4
17 | Golf Course |  | 1.4
18 | Golf Course |  | 2
19 | Golf Course |  | 5.3
20 | Golf Course |  | 3.5
21 | Golf Course |  | 2.3
22 | Golf Course |  | 3.2
23 | Golf Course |  | 2
24 | Golf Course |  | 2
25 | Golf Course |  | 0.5
26 | Golf Course |  | 0.7
27 | Golf Course |  | 0.7
28 | Golf Course |  | 1.3
29 | Golf Course |  | 1.2
30 | Golf Course |  | 2.3
31 | Golf Course |  | 1.1
32 | Golf Course |  | 2
33 | W. Lake |  | 1.3
34 | W. Lake |  | 0 | [6 empty] | Future pond, not active
35 | W. Lake |  | 0 | [6 empty] | Future pond, not active
36 | N. Lake |  | 0 | [6 empty] | Future pond, not active
37 | E. Lake |  | 3
38 | E. Lake |  | 0.5
39 | S. Lake |  | 3.3
40 | S. Lake |  | 1.4
41 | S. Lake |  | 2.3
42 | S. Lake |  | 5.2
43 | Waterside |  | 3
44 | DOT |  | 6
45 | DOT |  | 3.6
46 | DOT |  | 2
47 | Maintenance |  | 0.4
| TOTAL ACRES |  | 102.3 | Total size (in acres) of all ponds combined
| AVG. TREATED ACRES |  | 20.46 | Average treated pond area is roughly 20%
Scale: | L1-Traces/Controlled, L2-Partial Coverage/Controlled, L3-Partial Coverage/Uncontrolled, 4-Majorly or Completely Covered/Uncontrolled
Additonal Notes: