## Data
Harmony Community Development District
Field Services Monthly Wetlands Report
# | Maintenance Area Name | Acres | Invasive Species | 2020-01-23 | Treatment Status
| Map Tab Shows Local QuickMap |  | Vegitation Identification | (End-of-Month Status) | Pending Activities
| Click Links Below For Internet Maps |  | Infestation Severity High, Medium, Low | Prescribed Treatment | Percent Complete
1 | Buck Lake - South | TBD | Lygodium High | Spraying with mixture of RoundUp and Cutrine | 80 percent complete at this time Infestation larger than anticipated
2 | Green - South | TBD | Grapevine Medium | Sprayed with RoundUp and cut the vines running up the base of the trees | 100 percent complete
3 | Golf Course - West | TBD | Lygodium High
4 | Golf Course - East | TBD | Lygodium High
5 | Golf Course - South | TBD | Grapevine Medium | Spraying with RoundUp | Just getting started
6 | The Lakes - East | TBD | Lygodium High | Treating with RoundUp | Just getting started
7 | {Future} | -- | ----
8 | {Future} | -- | ----
9 | {Future} | -- | ----
10 | {Future} | -- | ----
11 | {Future} | -- | ----
12 | {Future} | -- | ----
13 | {Future} | -- | ----
14 | {Future} | -- | ----
15 | {Future} | -- | ----
| TOTAL ACRES | 0 | Total size (in acres) of all foliage maintenance areas
| AVG. TREATED ACRES | 0 | Average infested foliage treated area is roughly 20 %
| Additonal Notes: | We are getting close to the end on Buck Lake, but we have found three times the amount they surveyed. We have begun treatments on both the golf course and south lakes conservation area. A lot of the areas are taking two treatments to totally get rid of the lygodium because there is a massive blankets covering the ground and growing up the trees. We have to move around to different areas based on wind and weather for the days we are spraying. The results are good, and we have made a major impact on the areas that have been treated. There is a massive amount of fern and it is extremely difficult to reach in order to treat it.

## Map
Data!A1 | BACK

## MASTER (hidden)
Harmony CDD Monthly Pond Report
Pond # |  | Name | Acres | Duckweed | Algae | Cattail | Pennywort | Grasses | Spatterdock | Remarks | Treatment Plan
Map Quickview, click here. Internet access not required |  |  |  | SEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevance | [5 empty] | Color Code: ----> | Treated, current month
| Map links below require internet | [9 empty] | Treatment Needed
1 | H-1 |  | 1.4
2 | H1 |  | 1
3 | H-1 |  | 2.3
4 | H-2 |  | 3.7
5 | Cherry Hill |  | 2.8
6 | S. Long Pond |  | 3.1
7 | N. Long Pond |  | 3.1
8 | Dog Park Tr. |  | 3.5
9 | Dog Park Tr. |  | 1
10 | Dog Park |  | 3
11 | Estates N. |  | 1.8
12 | Estates S. |  | 1.7
13 | Golf Course |  | 1.5
14 | Golf Course |  | 1.5
15 | Golf Course |  | 4
16 | Golf Course |  | 3.4
17 | Golf Course |  | 1.4
18 | Golf Course |  | 2
19 | Golf Course |  | 5.3
20 | Golf Course |  | 3.5
21 | Golf Course |  | 2.3
22 | Golf Course |  | 3.2
23 | Golf Course |  | 2
24 | Golf Course |  | 2
25 | Golf Course |  | 0.5
26 | Golf Course |  | 0.7
27 | Golf Course |  | 0.7
28 | Golf Course |  | 1.3
29 | Golf Course |  | 1.2
30 | Golf Course |  | 2.3
31 | Golf Course |  | 1.1
32 | Golf Course |  | 2
33 | W. Lake |  | 1.3
34 | W. Lake |  | 0 | [6 empty] | Future pond, not active
35 | W. Lake |  | 0 | [6 empty] | Future pond, not active
36 | N. Lake |  | 0 | [6 empty] | Future pond, not active
37 | E. Lake |  | 3
38 | E. Lake |  | 0.5
39 | S. Lake |  | 3.3
40 | S. Lake |  | 1.4
41 | S. Lake |  | 2.3
42 | S. Lake |  | 5.2
43 | Waterside |  | 3
44 | DOT |  | 6
45 | DOT |  | 3.6
46 | DOT |  | 2
47 | Maintenance |  | 0.4
| TOTAL ACRES |  | 102.3 | Total size (in acres) of all ponds combined
| AVG. TREATED ACRES |  | 20.46 | Average treated pond area is roughly 20%
Scale: | L1-Traces/Controlled, L2-Partial Coverage/Controlled, L3-Partial Coverage/Uncontrolled, 4-Majorly or Completely Covered/Uncontrolled
Additonal Notes: