## Data
Harmony Community Development District
Field Services Monthly Wetlands Report
# | Maintenance Area Name | Acres | Invasive Species | 2020-02-25 | Treatment Status
| Map Tab Shows Local QuickMap |  | Vegitation Identification | (End-of-Month Status) | Pending Activities
| Click Links Below For Internet Maps |  | Infestation Severity High, Medium, Low | Prescribed Treatment | Percent Complete
1 | Buck Lake - South | 1.4 | Lygodium High | Spraying only with mixture of RoundUp and Cutrine. | Only small areas left to treat. Most are sprayed and dying.
2 | Green - South | 1 | Grapevine Medium | Sprayed with RoundUp & cut the vines running up the base of the trees. | 100 percent complete.
3 | Golf Course - West | 2.3 | Lygodium High
4 | Golf Course - East | 3.7 | Lygodium High
5 | Golf Course - South | 2.8 | Grapevine Medium | Treating with RoundUp. | Now treating one corner of area, but entire area needs treatment.
6 | The Lakes - East | 3.1 | Lygodium High | Treating with RoundUp. | Have starting spraying outside areas and will progress inward.
7 | {Future} | -- | ----
8 | {Future} | -- | ----
9 | {Future} | -- | ----
10 | {Future} | -- | ----
11 | {Future} | -- | ----
12 | {Future} | -- | ----
13 | {Future} | -- | ----
14 | {Future} | -- | ----
15 | {Future} | -- | ----
| TOTAL ACRES | 10.2317 | Total size (in acres) of all foliage maintenance areas
| AVG. TREATED ACRES | 2.0463 | Average infested foliage treated area is roughly 20 %
| Additonal Notes: | Buck Lake area has been along process most heavily covered areas have been sprayed now and is dying. We are working now on the smaller harder areas to reach which are requiring us to treat and access with backpack sprayers only. We have moved to large areas around the areas surrounding the large dog park as well as to golf course south behind swim club that is about 80 percent covered in lygodium; which over time now we have discovered must be treated a few times and also cut through to detach any remaining fern to kill all of it that is all the way up the trees. The only down side we have found is that we are already max'd out on our equipment and personnel.

## Map
Data!A1 | BACK

## MASTER (hidden)
Harmony CDD Monthly Pond Report
Pond # |  | Name | Acres | Duckweed | Algae | Cattail | Pennywort | Grasses | Spatterdock | Remarks | Treatment Plan
Map Quickview, click here. Internet access not required |  |  |  | SEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevanceSEVERITY: L1=minimal L2=moderate L3=significant L4=extreme - Blank indicates no relevance | [5 empty] | Color Code: ----> | Treated, current month
| Map links below require internet | [9 empty] | Treatment Needed
1 | H-1 |  | 1.4
2 | H1 |  | 1
3 | H-1 |  | 2.3
4 | H-2 |  | 3.7
5 | Cherry Hill |  | 2.8
6 | S. Long Pond |  | 3.1
7 | N. Long Pond |  | 3.1
8 | Dog Park Tr. |  | 3.5
9 | Dog Park Tr. |  | 1
10 | Dog Park |  | 3
11 | Estates N. |  | 1.8
12 | Estates S. |  | 1.7
13 | Golf Course |  | 1.5
14 | Golf Course |  | 1.5
15 | Golf Course |  | 4
16 | Golf Course |  | 3.4
17 | Golf Course |  | 1.4
18 | Golf Course |  | 2
19 | Golf Course |  | 5.3
20 | Golf Course |  | 3.5
21 | Golf Course |  | 2.3
22 | Golf Course |  | 3.2
23 | Golf Course |  | 2
24 | Golf Course |  | 2
25 | Golf Course |  | 0.5
26 | Golf Course |  | 0.7
27 | Golf Course |  | 0.7
28 | Golf Course |  | 1.3
29 | Golf Course |  | 1.2
30 | Golf Course |  | 2.3
31 | Golf Course |  | 1.1
32 | Golf Course |  | 2
33 | W. Lake |  | 1.3
34 | W. Lake |  | 0 | [6 empty] | Future pond, not active
35 | W. Lake |  | 0 | [6 empty] | Future pond, not active
36 | N. Lake |  | 0 | [6 empty] | Future pond, not active
37 | E. Lake |  | 3
38 | E. Lake |  | 0.5
39 | S. Lake |  | 3.3
40 | S. Lake |  | 1.4
41 | S. Lake |  | 2.3
42 | S. Lake |  | 5.2
43 | Waterside |  | 3
44 | DOT |  | 6
45 | DOT |  | 3.6
46 | DOT |  | 2
47 | Maintenance |  | 0.4
| TOTAL ACRES |  | 102.3 | Total size (in acres) of all ponds combined
| AVG. TREATED ACRES |  | 20.46 | Average treated pond area is roughly 20%
Scale: | L1-Traces/Controlled, L2-Partial Coverage/Controlled, L3-Partial Coverage/Uncontrolled, 4-Majorly or Completely Covered/Uncontrolled
Additonal Notes: